**IMPLEMENTATION SCHEDULE (Gantt-style Summary)**

**Project**: Odoo ERP Implementation  
**Organization**: Telco Net company.  
**Duration**: 6 months (can be adjusted)  
**Prepared by**: IT Project Manager  
**Date**: June 2025

**1. High-Level Phases & Timeline**

| **Phase** | **Key Activities** | **Duration** | **Start** | **End** | **Responsible** |
| --- | --- | --- | --- | --- | --- |
| 1. Initiation | Project Charter, Business Case, Stakeholder Approval | 2 weeks | Week 1 | Week 2 | PMO |
| 2. Planning | WBS, Risk Register, Change & Communication Plans | 3 weeks | Week 3 | Week 5 | PM |
| 3. Requirements Gathering | AS-IS vs TO-BE process analysis | 3 weeks | Week 6 | Week 8 | BA Team |
| 4. System Design | Module selection, configuration design | 2 weeks | Week 9 | Week 10 | Vendor & PM |
| 5. Development & Configuration | Customization, integrations, security setup | 6 weeks | Week 11 | Week 16 | Dev Team |
| 6. Data Migration | Extraction, cleaning, import into Odoo | 2 weeks | Week 17 | Week 18 | Data Lead |
| 7. Testing | Functional + UAT | 3 weeks | Week 19 | Week 21 | QA & Business Users |
| 8. Training & Adoption | End-user training, super-user support | 2 weeks | Week 22 | Week 23 | HR & Trainers |
| 9. Go-Live | Cutover, deployment | 1 week | Week 24 | Week 24 | PM & IT |
| 10. Post-Go-Live Support | Stabilization, feedback loop | 4 weeks | Week 25 | Week 28 | IT & Helpdesk |